## Tabelle1
checklist for your exhibition planning
01. | set corporate goals and expectations for upcoming exhibition participation
contact maintanance with existing customers
gain new customers
observe the competition
present new products
image cultivation
02. | choose team for this project
discuss the planned approach – everyone has to understand the set goals
define tasks and distribute them
03. | get the relevant documents from the organizers
technical guidelines
hall plan with supply shafts
plan with the suspension points
allowed building height in the hall
possible to build around hall pillars on stand
statics proof required
04. | plan your budget for this project, including renting the stand area, stand building, staff, marketing, hotels and PR
costs of renting the stand area
costs for logistics
payment of staff
hotels for staff
stand design, construction, furniture etc.
posters, banners, advertisements
insurances
power and water consumption
registration inside the catalogue of exhibitors
exhibitor Ids
05. | choose your exhibits
what do you want to present on this trade-fair
elements of the stand
furniture
technical devices
flyers, catalogues etc.
business cards and notepads
consulting checklists
cuttlery and drinks
legal papers (e.g. patents)
06. | request first stand design, define stand size and kind und Standfläche buchen
front stand
corner stand
inline stand
joint stand
island stand
choose stand in a specific hall
07. | stand planning (order a system stand or decide on stand building company for your individual stand)
design (company colours)
photos of past stand designs
lighting
signs and lettering
media technology
furniture
kitchen (cuttlery, coffee machines)
consistent design
obviously we woud love to take care of your stand planning for you
08. | define marketing services and channels considering your trade-fair appearance (adverts before, during and after the exhibition, online and in the exhibition halls)
set adverts referring to the exhibition, as well as the platforms
choose the magazines
promote your appearance on your website
promote your appearance in your email signature
exhibition catalogue
09. | check supporting programme of the trade-fair (possibilities for speeches, evening programe, etc.)
10. | cast staff for your stand
one head of stand management
language abilites (if you are expecting foreigners)
prepare your staff for specific tasks (training if necessary)
competent contact person
draft a working schedule for your staff
define your work clothes, name tags and logo
if exhibition is abroad remember to have valid passports
11. | organize hotels and travels
12. | stand order
power
water
communication (wifi etc.)
cleaning
catering
suspension points
stand construction permit
parking spots
we can also do this for you
13. | order exhibitor IDs and ticket vouchers, if necessary paring IDs
14. | invite your customers
15. | organize logsitics and storage of your exhibits
16. | prepare docsuments to fill in contact forms
business cards
company magazines
flyers
references
17. | handover of your stand
set a date with your exhibition building company
set up your stand (move exhibits and brochures)
take photos or let photos be taken of your stand
18. | follow-up work and analysis - IMPORTANT
compare turnovers
sum up gained knowledge of the market and competitors
can the stand design be improved
collect all critics of customers
can personnel planning be improved
did we have the right/enough brochures and exhibits
has the budget been crossed or fallen short
did we gain new customer categories
did we gain experience according our products or industry
19. | rework customer contacts - IMPORTANT
send offers
information
thank you notes
all in between the next week